LEARNER INFORMATION

CMI LEARNER STATEMENT/DECLARATION OF AUTHENTICITY

### This statement must be completed and electronically attached to the completed assessment submitted to CMI. Any pieces of work that do not have this signed statement/declaration are inadmissible and will be returned to the Centre.

Section 1 -

| ### Qualification Title | ### Management Level 5 – Management and Leadership |
| --- | --- |
| ### Unit Number and Title | ### HTQ Unit 553 – Operational Planning |
| ### Centre Name | ### Weston College |
| ### Learner Name | ### Graeme Wright |
| ### Learner CMI Number | ### P05260463 |

I, Graeme Wright confirm that the work submitted is my own and that I am the sole author of this completed assessment and Sections 1 & 2 of this form have been checked and completed before submission. I have referenced/acknowledged any sources of information and Artificial Intelligence (AI) tools used in the submission; in line with the Qualification Handbook, CMI's Assessment Guidance Policy and CMI’s Plagiarism, Collusion and Artificial Intelligence (AI) Statement.

| I consent to this assessment, or any extract from it, to be anonymised following which it may be used for assessment standardisation and, where appropriate, for the dissemination of good practice. The assessment will be kept in accordance with GDPR, if you have any concerns regarding this, please refer to our Data Privacy Policy | Tick here to opt-out |  |
| --- | --- | --- |

Section 2 -

| Requirement prior to submission | Learner Signature / Initial to confirm |
| --- | --- |
| The Assessment Criteria (AC) have been used as headings or I have indicated or sign-posted within my work where each AC has been met. |  |
| Word count is shown on the front sheet and is within the CMI guidelines for the unit. |  |
| All answers relating to the Assessment Criteria (AC) are contained within the body of the text. |  |
| Learner name and CMI membership number are identified on each page within the assessment (header or footer) and each page is numbered. |  |
| All work that is not my own is clearly indicated and referenced using a formal referencing system. |  |
| The work has been reviewed for spelling and grammar. |  |
| Where work has been translated, the accuracy of the translation has been checked. |  |
| I understand that CMI may use plagiarism software in the detection of plagiarism, collusion and AI misuse for this submission. |  |

### I understand that a false declaration is a form of malpractice.

| ### Learner Signature* |  |
| --- | --- |
| ### Date (DD/MM/YYYY) | ### 30/08/26 |

### *Please note electronic signatures are accepted

ASSESSMENT TASKS AND WORD COUNT

Assessment brief CMI HTQ 553 features the following assessment tasks. Further detail is provided against each assessment task within the brief. Assessment Task; Learning outcomes covered by assessment method; Assessment criteria; 5 ODM KSB; Guideline word count. 1; Write an report titled ‘The principles of operational planning’; LO1 Understand the principles of operational planning in an organisation; 1.1 Assess the relationship between an organisation’s strategic objectives and operational planning; K1 K2; Approx. 2500 words. 1.2 Evaluate the use of approaches to operational planning. LO2 Know how to create an effective operational plan; 2.1 Assess methods of managing and leading the delivery of an operational plan; K3 K18. 2.2 Review techniques for problem solving and decision making; K19. 2.3 Assess the ethical requirements that influence an operational plan; K20. 2; Create an Operational Plan covering a minimum of three months; LO3 Be able to manage and lead the delivery of an operational plan; 3.1 Create an operational plan in line with organisational objectives; K1 K3 K18 K19 S1 S3, S4 S5, S6 S15 S16 B1, B2 B3, B5 B4; Approx. 1500 words. LO4 Be able to monitor and measure the outcome of operational planning; 4.1 Evaluate methods used to monitor progress and measure the outcomes of operational plans. 4.2 Examine the impact of legal and organisational factors on an operational plan.

Guideline word count

The written word, whether generated and/or recorded, is expected to form the majority of assessable work produced by Learners at Level 5. The amount and volume of written work for this unit should be broadly comparable to a word count of 4000 words within a margin of +/-10%. The unit also includes additional work in the form of work based evidence. Excessive use of word count is not grounds for referral, however, the CMI reserves the right to return work to the Centre for editing and resubmission by the Learner.

The following are excluded from the written word count: Index or contents pages, headings and subheadings, diagrams, charts and graphs, bibliography.

Please see the CMI Assessment Guidance Policy for further guidance, along with the guidance on Command Verb Definitions.

LEARNER EVIDENCE

# Unit 553. Task 1: The Principles of Operational Planning Frame: The Digital Leads accessibility and inclusion programme. Organisational objective (College QIP 25/26): "Ensure the SEND Framework permeates the organisation and that TLA is inclusive for all." Plan period for Task 2: September – November/December, with the November audit as checkpoint. ## AC1.1: Assess the relationship between an organisation's strategic objectives and operational planning The gap between knowing and doing Before this programme, work on inclusion focused on frameworks and pedagogy rather than on the practicalities of making learning materials accessible. The analogy I use is a kitchen: we all know how to clean one and we understand the benefits of a clean kitchen, but we don't enjoy doing it, so we stop, and eventually the kitchen is filthy. Accessibility is much the same. We know that headings should be structured, that images need alt text, that resources should be readable by a screen reader. We know about Immersive Reader. But we do not consistently do what is necessary to enable learners who need assistive technology to use it. Pfeffer, J. and Sutton, R.I. (2000) The Knowing-Doing Gap: How Smart Companies Turn Knowledge into Action describes exactly this: organisations know what to do and do not do it. A typical example is that staff tell me they know about Immersive Reader. When I ask whether their students know about it, since they are the ones who need it, the answer is usually no. When I follow up by asking whether their resources are built so that students can use assistive technology effectively, the answer is usually "how do I do that?" Argyris, C. and Schön, D. (1974) Theory in Practice: Increasing Professional Effectiveness identifies this gap between what we assert we know and the detail and skill required to act on it. The college has done substantial work on the SEND Framework and Quality First Teaching. What has been missing is the detail and the foundations that allow those things to work, which the Jisc Discovery question set in December and the Digital Lead audits in July and August have made visible. Translating the objective into deliverables The relevant organisational objective is to "ensure the SEND framework permeates the organisation and that TLA is inclusive for all." This has been translated into specific requirements. Staff produce learning materials that are accessible by design. Digital learning environments are easy to navigate and reduce the clicks needed to reach material. Learning content is captured digitally to support learner independence, which builds on accessible design rather than replacing it. Alongside this sits how materials are shared, and how safe and communicative environments are maintained through Microsoft Teams. I have also developed resources for learners and staff on the assistive technology already available on their own devices: Read&Write, dictation, Immersive Reader, and closed captions. Both groups are necessary. Accessible materials have limited value if learners do not know the tools exist, and knowing the tools has limited value if the materials will not work with them. Accessible materials are therefore a precondition for the SEND framework permeating practice, because assistive technology cannot work effectively on inaccessible content. The feedback loop Findings feed back through three levels of reporting. I report to my line manager, the Assistant Principal for Quality, on the detail: work undertaken, what has been identified, action plans proposed, impact, and who I have worked with. I report to the Vice Principal for Quality at a collegiate level: the scale of the problem, RAG ratings, audit completion, which areas need most support, and what impact previous work has had. I also have upcoming meetings with the Deputy Principals responsible for learner experience and learner outcomes. These extend beyond learning materials, addressing the need for non-teaching roles, including the executive team and Professional Learner Services, to receive training on accessibility and inclusion, so that the foundations for the SEND Framework are in place across the organisation rather than in teaching alone. This illustrates that the relationship between strategic objectives and operational planning runs in both directions. The objective set the direction, but the operational data has changed the understanding of what achieving it requires. ## AC1.2: Evaluate the use of approaches to operational planning I deliberately designed this programme around Deming's Plan–Do–Check–Act cycle, Deming, W.E. (1986) Out of the Crisis, MIT Press, Cambridge MA. Its strength is that it supports iterative development, which suits how I work: I develop plans, strategies, ideas and resources iteratively, based on reflection, feedback and evidence of impact. It is slower than a linear approach, but measuring against a baseline set of data gives clarity about where impact has been achieved, and identifies where action will have the greatest effect. I have worked with Gantt charts before, and I still plan on the principle of building phases towards a target. This helps me stay on top of progress and deadlines, and allows measurement at the right milestone points. Its limitation is that it assumes a degree of control I do not have. Teaching timetables, the availability of other departments, and factors outside my remit all affect the sequence. The programme also relies on resource and capacity planning. I cannot do this work alone across 600 staff, so building a network of 36 volunteer Digital Leads extends reach across a far wider scope of the college. The limitation is obvious: they are volunteers with existing teaching commitments, and engagement will vary. Even if only half work enthusiastically where I need them to, this significantly reduces my workload and helps the college move more quickly towards the foundations needed to support the SEND Framework and the inclusive practice identified in the Ofsted toolkit. Put simply, even one volunteer working well extends my reach and accelerates impact. Of the three, capacity planning is the approach that carries the programme. I recognised early that it would be impossible to understand the position of the college on accessibility and inclusion without first building a network of volunteers who could help identify what the landscape actually looked like, what the specific issues were, and what an action plan for their area and staff should contain. It is the capacity planning that makes Deming's PDCA cycle possible at all; without the network there is no way to gather the data that the "check" stage depends on. This has also proved differentiated in practice. Some Digital Leads receive an action plan reflecting their own audit findings, with guidance on improvements, and are content to run with it themselves. Others need me to talk through the process, the patterns in their data and the actions arising before they implement. Others need me to be directly involved in training and development with their staff. Capacity planning has therefore allowed me to build a picture across the college far more rapidly than I could alone, while also identifying where Digital Leads can take ownership in their own areas and grow into leadership roles. ## AC2.1: Assess methods of managing and leading the delivery of an operational plan To manage and lead delivery of the plan I have used a differentiated model, with the Digital Leads at the centre of driving the programme. It follows Hersey and Blanchard's situational leadership model, matching my approach to each volunteer's readiness and capability in the role: directing someone new to the role, coaching them as they develop, supporting them when they are capable but hesitant, and delegating when they are both able and willing. Hersey, P. and Blanchard, K.H. (1993) Management of Organizational Behavior: Utilizing Human Resources, Prentice Hall, Englewood Cliffs NJ. Its limitations are that it assumes I can recognise readiness accurately, and that it is demanding on my time, since I am running several styles at once. The main problem I encounter is that I am not a line manager within this programme, so there is less accountability. Where this matters I lean on the leadership above me: my own line manager, who leads on quality improvement, and the Vice Principal for Quality. With their support, if an action plan is not followed through, or is not being implemented by a team, there is a route through Heads of Area, who do hold line management responsibility for the Digital Leads, to ensure the actions are carried out. Visibility is deliberately built into the process for this reason. I report Health Check completion rates and RAG ratings by area to the Vice Principal for Quality. I am uncomfortable with the idea of reporting on colleagues, but patterns become obvious when work has been asked for and not done, and making that visible at a level above the Head of Area means accountability does not have to rest on me personally. Those with the authority to act can then direct what I do next, allowing me to carry their name in my communications, or engage someone else with the appropriate authority to act on my behalf. My preferred approach reflects the leadership style identified through Insights Discovery. I work collaboratively to find where barriers exist and support people in removing them, rather than leading with direct authority. In previous roles I have found this generates better buy-in and more sustained impact, and that building relationships this way allows colleagues and me to work more innovatively. Contact varies. Some Digital Leads I meet more regularly than others, but I communicate with all of them at least weekly or fortnightly to understand where they are, what issues or barriers have arisen, and what their reality looks like. This means that if a task has not been completed, I already understand the context. A department may be carrying staff absence, with everyone covering additional workload, so lower-priority tasks get pushed back. Understanding the day-to-day context of Digital Leads in their departments helps me judge what is realistic rather than simply what was expected. My intention is to report back to Digital Leads directly, so that they can report to their own Heads of Area. This raises their profile and supports their development into leadership pathways, while allowing a differentiated approach: a lighter touch with those who are more experienced, and a stronger coaching role with those who are less so. ## AC2.2: Review techniques for problem solving and decision making Root cause analysis. Throughout the planning and discovery phase I identified that accessibility was a problem, but I made assumptions about the root cause. I assumed staff knew the basics and simply were not doing them, and that this was down to a lack of time or slipping into bad habits. What the audit revealed is different. Staff regularly told me they understood accessibility and did not need training, but further enquiry showed they were not meeting basic standards. We know the language of accessibility and inclusion, but not the functions that make something accessible, or how to share resources so that learners can use assistive technology against them. We know Immersive Reader exists and we promote it, but the next step is missed: how the learner reaches the material, and whether the resource has been built so that it works well when assistive technology is used. My conclusion is that we have oversimplified accessible and inclusive practice, and are now in danger of overcomplicating something fundamental. Immersive Reader is covered in induction in September and never revisited. This matters more now because increasing numbers of learners arrive from secondary school with poor digital literacy, many having stopped using computers after Year 9, so a single introduction is not enough. Data-driven decision making. The Digital Health Check audit exists precisely so that decisions are not made on best guesses. The data tells me what the issue is, where it is, what action is needed and how urgently. In some departments I have offered whole-team training; in others I have suggested the Digital Lead puts forward a named member of staff for half an hour of one-to-one coaching on designing accessible materials. Prioritisation and triage. I built a system to RAG rate areas so I can prioritise where the greatest impact is available. I am currently focusing on two. English, because their learners are largely retaking GCSEs having not achieved a grade 4 at secondary school, and are therefore learners who may already have faced barriers. Where we provide digitally inaccessible material, or material that induces cognitive overload, we add another barrier, and the likely response is to disengage. Redesigning that material makes curiosity and confidence more likely. The second is SEND, whose expert knowledge of supporting learners with additional needs is exceptional, but whose own materials and communications are often inaccessible. Given their reach across the college and the organisational objective that the SEND Framework permeates every part of it, that work would be foundational. Consultative decision making. I have worked with Jisc and the community I belong to within it to refine my approach, particularly learning from others attempting to drive organisational change without authority or accountability metrics: how to nudge people towards chosen behaviours rather than instruct them. This approach is consistent with Thaler and Sunstein's concept of choice architecture, where behaviour is influenced by how options are presented rather than by mandate. Thaler, R.H. and Sunstein, C.R. (2008) Nudge: Improving Decisions About Health, Wealth and Happiness, Yale University Press, New Haven. Alongside SEND consultants and my own research, this informs the decisions I take. Iterative review. The PDCA cycle runs throughout, keeping the programme reflective and checking that what we are doing remains fit for purpose rather than continuing down a road because it looked right at the outset. This matters because external factors (Ofsted inspection, departmental restructuring) sit outside my control and carry higher priority than this programme. ## AC2.3: Assess the ethical requirements that influence an operational plan Equality of access. The most significant ethical requirement is equality of access. Framed as making learning materials accessible by design, it can sound like a nice-to-have. Framed the other way round, by understanding why those learners need assistive technology in the first place, the question becomes why we are not treating it as an absolute priority that everything we produce is built with them in mind. We are currently failing our most vulnerable learners, whether through time pressure, poor habits, or lack of knowledge. For me this is foundational: everything else sits above it, and until it is right, the work above it is compromised. That is not the current reality, but it is the central ethical issue in this plan. There is also a legal dimension. The Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018 apply to further education institutions, which are considered in scope through their dependence on public funding. Significantly, the regulations extend beyond public-facing websites to intranets, extranets, virtual learning environments and the digital content held on them, including documents, presentations and eLearning resources. The standard required is WCAG 2.1 AA. Content published before 23 September 2019 is exempt until it undergoes substantial revision, which means that material staff create or update now falls within scope. These regulations sit alongside the Equality Act 2010 duty to make anticipatory reasonable adjustments. Jisc (no date) Accessibility regulations – what you need to know. Available at: https://www.jisc.ac.uk/guides/accessibility-regulations-what-you-need-to-know (Accessed: 30 August 2026). I have had recent discussions with leaders who were not aware of these requirements, which is itself an ethical issue: we cannot expect staff to meet standards that the organisation has not clearly communicated. Reporting on colleagues. I find it difficult to report on colleagues without first having done everything I can to support them. This is one reason I keep communication lines open and offer help consistently and informally. It is also practical. When I hand a visible report to the Vice Principal and am asked why a department has completed none of the required actions, I need to be able to answer that question. So the obligation runs two ways: supporting colleagues to meet the requirements so that their departments and learners benefit and the organisational objective is advanced, and ensuring I cannot fairly be accused of failing to support colleagues over whom I have no management responsibility. The volunteer relationship. The Digital Lead role is voluntary, but it was put to Heads of Area that someone in their team would need to take it on, and that if nobody did, it would fall to them. It is unpaid, which creates an obligation to invest in those people in other ways. There are opportunities to attend educational conferences on digital learning in London and Birmingham, and ten members of staff will be offered coaching qualifications. I am also developing recognition: branded items such as hoodies or lanyard badges, a logo for email signatures, presence in the monthly staff newsletter, and a space on our internal SharePoint identifying the Digital Leads and showcasing their work. Alongside this, I want them to understand the significance of what they are doing. The way I explained it to one group drew on my previous work as a sound engineer: if I did not do my job with integrity and care, the artists on stage would not sound good. Nobody in the audience recognises the sound engineer's work, but it is the sound engineer who makes everything else work. Honesty in the baseline. I made clear in the baseline audit that we wanted to see the true state of things, including everything that was uncomfortable. An audit designed to produce reassuring results would be worthless, and would remove any ability to demonstrate improvement later. Being honest about the starting position is what allows even small improvements to be visible and meaningful. # Unit 553. Task 2: Operational Plan ## AC3.1: Develop an operational plan for an area of work Why this area of work. I was originally employed as Digital Coach and later reassigned as Digital Pedagogy Coach. In my first nine months I found that many staff did not have the fundamentals in place that would allow digital pedagogy to elevate their teaching, and accessibility was where the weakness sat. I want to work in the innovative space around digital learning, but that is not possible while the foundations are unstable. It is like building a beautiful modern house on sand. Requests for help with innovative practice frequently unravel, on examination, into gaps in understanding of how to design learning for a range of needs. Some needs are documented through EHCPs, so we can plan for them. Others are situational and invisible. If I break my glasses, I need a screen reader or larger text. The dropped kerb was designed for wheelchair users and is now used by people with pushchairs, bicycles, delivery trolleys and anyone less steady on their feet. A personal example: when my daughter was small and I fed her in the night, I could not read a document and did not want a lit screen in the room, so I used read-aloud through headphones. Nobody designed that adjustment for me. We do not know our learners' situations either. Designing all learning material accessibly from the point of creation is measurable, and it allows everything else to sit on top: how resources are shared, how they are personalised, and how the organisation communicates through policies, marketing and stakeholder communication. Resources. This requires a significant amount of my time. I work closely with the Accessibility Manager and with SEND consultants, and am currently discussing relocating my office into the SEND team's space so that the accessibility work and the SEND Framework work operate alongside each other daily. I retain other responsibilities within the Quality team, including learning walks and staff coaching. The ambition of being fully accessible and inclusive by the end of the academic year may not be fully realised, but if we keep moving in that direction we will be left with a small number of individual situations to address rather than an organisational one. Budget. A small budget is held by my line manager, who approves requests. It covers transport for conference attendance in London and Birmingham, Level 3 coaching qualifications for ten staff, and recognition materials. I do not hold the budget figures directly, which is a limitation of the plan at my level of authority. Communication. Communication runs through the staff newsletter, the internal SharePoint, the established reporting tiers, and Teach Meets delivered in departments. I communicate with Digital Leads individually through Teams, and maintain a dedicated Digital Leads team space for messages, resources, direction and deadlines. Contingency. If a Digital Lead withdraws, the Head of Area assumes the responsibility until a replacement is found. This has already occurred in several departments, where Heads of Area could not recruit a volunteer, and in one case where a Digital Lead withdrew rather than be accountable to an audit. If the November audit shows no visible improvement, the barriers will be re-examined and escalated. The current operating assumption is that staff know what to do and are not doing it. If the November data shows they genuinely do not know how, the model changes deliberately: from nudging towards correct behaviour to teaching at a basic level. A plan rather than an ambition. This is a plan rather than a hope because we have baseline data to measure against, a defined path, mechanisms to move it forward, and checkpoints to confirm we are progressing at the right pace. We have ways to identify barriers so that other departments or experts can be brought in, and fallback arrangements so that if people leave post the work continues without losing momentum. ## AC4.1: Discuss methods used to monitor and evaluate the operational plan Monitoring is designed as a repeating cycle rather than a single before-and-after comparison. The June–August audit establishes the baseline; November is the first re-audit point, with further cycles in February and May, so each round measures against the last rather than against a one-off snapshot. This allows me to ensure we stay on the right path and keep reflecting on the PDCA model previously discussed. Monitoring and evaluation does not rest on the November re-audit alone, although that is the primary instrument. Re-auditing against the same Health Check indicators produces a directly comparable data set: revised RAG ratings by area, improvement scores for individual members of staff, and area averages against the June–August baseline. Relying on that alone would be a weakness. The audit is a self-assessment carried out by Digital Leads, and improvement in scores could reflect changed practice or simply changed judgement on a second pass. Evaluation is therefore triangulated through several lenses and aligns to Brookfield’s four lenses (discussed in Unit 554 AC1.3). Learning walks provide observation of practice by someone other than the Digital Lead. Learner feedback samples test whether changes have been experienced by the people they are intended to benefit. Direct sampling of resources allows the materials themselves to be examined rather than reported on. Alongside this, the wider Quality team will pick up an element of this work with a quality focus, which places the evidence outside my own function. These arrangements are currently in discussion with my line manager rather than confirmed. The intention is that improvement is visible through a variety of lenses, rather than resting on a single self-assessment instrument. Where a re-audit shows a department has gone backwards, the Quality team has an established escalation route. We work intensively with the area, bringing the Head of Area into the discussion, agreeing an intensive action plan, and arranging Teach Meets and other required activity. The area is then seen very regularly over a short period, so that practice can be corrected quickly rather than left until the next cycle. The baseline audit ran across July and August, though some areas are still completing it against an expected end-of-July deadline. This is itself a compliance issue, and one with a real consequence: an area that has not established a baseline cannot demonstrate improvement in November, and its non-completion becomes visible at the point when the Quality team looks at the data. Operationally, however, the staggered completion has an advantage, since receiving every audit simultaneously would create a workload peak in producing action plans for all areas at once. Beyond November, the plan runs on a recurring cycle, with further audit points around February and again in May or June. The intention by the end of the academic year is that teaching areas across the college know how to design learning materials accessibly, that learners know how to use the assistive technology available to them, and that barriers to learning are reduced through improved inclusive practice. Digital learning environments are the next phase rather than part of this one. Current practice varies considerably: some areas maintain well-structured Teams spaces, others use a single channel containing everything, others barely use them, and in some cases all documents sit in one folder with editing permissions open to the whole team including learners. Addressing that follows the work on learning materials, after November. ## AC4.2: Assess the impact of legal and organisational factors on an operational plan Legal factors. The plan is shaped by WCAG 2.1 AA, the Public Sector Bodies Accessibility Regulations 2018, and the Equality Act 2010. Material published before September 2019 is not required to be compliant until substantially revised, but that is now seven years ago and most material has changed since. The practical impact is a sequencing decision: my plan is to ensure all newly created material meets the standard from now until January, then work back retrospectively through older material. An unresolved legal question has been raised by Digital Leads and Heads of Area. Some awarding bodies require the use of their own materials and assignment briefs. These are often legacy documents, they are inaccessible, and they do not meet the required standards. Our Accessibility Manager is keen to raise this with awarding bodies to ensure that what we provide meets standards regardless of origin. I have deliberately parked this until internal material is addressed, since it is outside our direct control and would divert effort from work we can complete. The Equality Act dimension is one of equity: some learners have better access than others. Learners are entitled to use Read&Write and we hold licences, but it is difficult to deploy to learner machines, so installation falls to the user. The learners most likely to need it are the least likely to have the digital confidence to install it, so they depend on teaching staff who are frequently unaware that Read&Write exists or how to find it. Organisationally this is difficult, because the communication and process sit with a different department. The impact on my plan is a dependency I cannot resolve directly. The audit has also surfaced a GDPR issue. Some tutors lack confidence in managing their Teams learning environment, and in one case learners' one-to-one notes were held where the whole team could access them. Not only view them, but edit them. This required immediate correction with the member of staff concerned. It illustrates that the plan's scope extends beyond accessibility into data compliance. Organisational factors. Legal compliance strengthens the argument for the work. Staff sometimes ask whether this is being done for Ofsted. It is not only for Ofsted, or to evidence inclusion more effectively. It is for learners, their experience and their confidence, which is the human argument. But providing non-compliant material through a virtual learning environment is also serious and urgent in its own right. My concern is how well this is understood by those in positions of power. Part of the purpose of this programme is to reach Vice Principals and Deputy Principals, and for that understanding to cascade to Heads of Area and Digital Leads. I need to inform those with authority that this is urgent, and to enable those in a position to act. I can then work with Heads of Area, Digital Leads and their staff to ensure people have the training and knowledge to make the changes. Competing priorities also affect the plan. An Ofsted inspection is expected, and will take precedence. Considerable additional evidence will be required on how we manage learners' education and monitor baseline skills and progress, particularly in English, maths and digital skills. This creates an opportunity as well as a pressure: digital now has a route into inclusion, and also into the baselining and monitoring of English, maths and digital skills progression.

BIBLIOGRAPHY

Unit 553: Bibliography

Argyris, C. and Schön, D. (1974) Theory in Practice: Increasing Professional Effectiveness. San Francisco: Jossey-Bass.

Deming, W.E. (1986) Out of the Crisis. Cambridge, MA: MIT Press.

Equality Act 2010, c.15. Available at: https://www.legislation.gov.uk/ukpga/2010/15/contents (Accessed: 30 August 2026).

Hersey, P. and Blanchard, K.H. (1993) Management of Organizational Behavior: Utilizing Human Resources. 6th edn. Englewood Cliffs, NJ: Prentice Hall.

Jisc (no date) Accessibility regulations – what you need to know. Available at: https://www.jisc.ac.uk/guides/accessibility-regulations-what-you-need-to-know (Accessed: 30 August 2026).

Ofsted (2025) Further education and skills inspection toolkit. Available at: https://assets.publishing.service.gov.uk/media/68b975aa3f3e5483efdba9c3/Further_education_and_skills_inspection_toolkit.pdf (Accessed: 30 August 2026).

Pfeffer, J. and Sutton, R.I. (2000) The Knowing-Doing Gap: How Smart Companies Turn Knowledge into Action. Boston, MA: Harvard Business School Press.

The Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018, SI 2018/952. Available at: https://www.legislation.gov.uk/uksi/2018/952/contents (Accessed: 30 August 2026).

Thaler, R.H. and Sunstein, C.R. (2008) Nudge: Improving Decisions About Health, Wealth and Happiness. New Haven, CT: Yale University Press.

Weston College (2025) College Quality Improvement Plan 2025/26. [Internal document].

World Wide Web Consortium (2018) Web Content Accessibility Guidelines (WCAG) 2.1. Available at: https://www.w3.org/TR/WCAG21/ (Accessed: 30 August 2026).

Unit 553: Statement on the use of AI

I used Claude (Anthropic) as a learning support tool throughout the preparation of this assignment. The nature of that support was as follows.

Understanding the brief. The assessment criteria and command verbs were explained to me, including the distinction between "assess", "evaluate", "review" and "discuss", and what each criterion required me to demonstrate.

Drawing out content. I was asked structured questions about my own work, and I responded verbally using dictation. All examples, evidence, professional judgements and reflections in this assignment are my own.

Editing my dictated text. My dictated responses were returned to me tidied for grammar, spelling, repetition and order. Dictation errors were corrected (for example "Cobb" for "Kolb", "Quality Act" for "Equality Act"). I reviewed and approved all edits, and made substantial further changes of my own.

Sources and referencing. Along with my own reading, and learning through Mindful, and my use of academic research in my responses and notes, additional relevant academic sources were suggested to me, along with guidance on where they supported my argument. I have verified each source and satisfied myself that it says what I have attributed to it.

Verification and challenge in both directions. Factual claims were checked against published sources rather than accepted from either party. Where my own figures were wrong, this was identified and corrected: I had stated staff numbers as 6,100 when the correct figure is 600+. Equally, where the AI's position was wrong, I challenged it and required it to verify. On the application of accessibility requirements to learning materials, I was advised that my claim was an overstatement; I held my position, asked for it to be checked against published sources, and my understanding was confirmed to be correct. The Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018 extend to intranets, extranets, virtual learning environments and the digital content held on them. The version in this assignment reflects the verified position. This process of mutual challenge is what gives me confidence that the sources, claims and analysis presented here are accurate.

Data and tables. Figures 1–8 were compiled from my own working data, including the Digital Health Check schema, the area RAG framework, and the June–August 2026 baseline audit records held in the Digital Pedagogy Coach Hub. Descriptive statistics in Figure 3 were calculated from that data. The audit instrument, the data and the operational plan are my own work.

Critical feedback. I received challenge on the accuracy and strength of my drafting, including where claims were unsupported, where word counts were exceeded, and where my proposed key performance indicators were methodologically inconsistent. I acted on that feedback.

The analysis, the professional judgements, the operational plan and the conclusions in this assignment are my own.

WORK BASED EVIDENCE

Work Based Evidence - U553.docx