## Slide 1
Approaches to Change Management
Digital skills support at Weston College: rationale, embedding, leadership and engagement
Graeme Wright | Digital Pedagogy Coach | CMI HTQ Unit 552
Notes: This presentation examines recent structural change at Weston College and the transition of digital skills support: why the change was initiated, how it is embedded and sustained, the role of leadership in overcoming barriers, and why stakeholder engagement runs throughout.

## Slide 2
Why change was necessary: external drivers
AC2.1
Regulatory
The Ofsted toolkit embeds digital skills in the graded Achievement descriptors, and inclusion now stands on its own.
Legal
SEND framework,
WCAG 2.1 AA
Equality Act 2010
require assurance over materials and the digital environment.
Economic
Flat funding settlements and a contract not renewed.
Compliance could not be bought, so it had to be restructured.
Analysed using PESTLE (Aguilar, 1967)
Notes: The rationale for change came from a collision of external pressures, analysed here using PESTLE (Aguilar, F.J. (1967) Scanning the Business Environment, Macmillan, New York). Regulatory pressure came first. Ofsted's updated toolkit embedded digital skills into the graded Achievement descriptors, and inclusion gained its own standing. Alongside the SEND framework, WCAG 2.1 AA and the Equality Act 2010, this required assurance over both the material we produce and the digital learning environment itself, principally Microsoft Teams. Economic pressure followed. Flat funding settlements meant the college could not buy its way into compliance, and a decision not to renew a substantial contract meant savings had to be found internally. Restructuring became the route to meeting new external demands.

## Slide 3
Why change was necessary: internal drivers
AC2.1
What staff believe
That they are competent in digital practice, including accessibility.
What the evidence shows
Awareness-based indicators score higher than those requiring learned technical action.
The knowing-doing gap (Pfeffer and Sutton, 2000)
Structural fragility
Digital pedagogy expertise concentrated in a single specialist post, now within Quality. A critical single point of failure across 35 areas, nine campuses and 600+ staff.
Cultural gap
Jisc Discovery data from December showed high confidence alongside limited objective competence, meaning the college drifted out of alignment with expected compliance.
Notes: Internally, capability and structural gaps made change inevitable regardless of external pressure. Digital pedagogy expertise was concentrated in a single specialist post, now within Quality, creating a critical single point of failure across an organisation of this size. Culturally, baseline data revealed a pronounced knowing-doing gap (Pfeffer, J. and Sutton, R.I. (2000) The Knowing-Doing Gap, Harvard Business School Press, Boston). The Jisc Discovery data gathered in December showed high staff confidence in digital capability alongside limited objective competence. Staff did not know how to do what they believed they understood, which meant the college was drifting out of alignment with its own Quality Handbook.

## Slide 4
From project to business as usual
AC2.2
Change dies when it is a one-off event. It survives when it is anchored in culture and process.
1
Taught once, at induction
Assistive technology is introduced alongside everything else, at the most overwhelming point of the year.
2
It never becomes normal practice
Access arrangements must reflect a learner’s normal way of working. A laptop cannot be given in an exam to someone who has never used one.
3
The learner loses an entitlement
No embedded practice means no evidence, and no evidence means no adaptation.
Notes: For change to survive in a college it must stop being a project and become business as usual. Change quietly dies when it is delivered as a one-off training event, and survives only when anchored into culture and operational process (Kotter, J.P. (1996) Leading Change, Harvard Business School Press, Boston). Accessibility illustrates this. Assistive technology such as Immersive Reader has historically been introduced once, at induction, alongside everything else a learner must absorb at an overwhelming point in the year, so it never becomes normal practice. That matters because examination access arrangements must reflect a learner's normal way of working: a learner cannot be given a laptop in an examination if they have never used one. Teaching a tool once a year does not embed it, so the evidence needed to secure the adaptation never exists and the learner loses an entitlement.

## Slide 5
Mechanisms that actually embed
AC2.2
Quality Handbook
Writes the expectation into formal standards and brings work scrutiny, learning walks and learner voice to bear. Structural, not optional.
Digital Leads
Socialises change peer-to-peer inside departments. More durable than directive.
Health Check cycle
Institutionalises the change so it survives any individual. Revisited and measured annually.
Why change fails here: change fatigue, and reliance on a single champion. When the Digital Education Manager post went, the framework lost its champion.
Notes: Not every mechanism embeds behaviour. Publishing SharePoint assets delivers content; it does not change practice. Two mechanisms do. Aligning digital skills to the Quality Handbook makes the change structural rather than optional, and brings existing assurance activity to bear: work scrutiny, learning walks and learner voice triangulate whether behaviour has changed. The Digital Leads programme socialises the change, reinforcing habits peer-to-peer within departments, which is more durable than directive. Change fails to stick for two reasons: change fatigue after eighteen months of restructuring, and reliance on a single champion. When the Digital Education Manager post went, the framework lost its champion and ownership passed to a colleague who had to be brought up to speed, slowing the work considerably. Change must therefore be institutionalised rather than personalised, which is why the annual Digital Health Check cycle forces the college to revisit and measure it every year.

## Slide 6
Leadership without authority
AC2.3
Mandate
Assumes positional authority and budget control. Orders compliance. Was never available to me.
Influence
Listen to the fear, then answer it structurally. The staff-hold-their-own-data model built the psychological safety that made honest engagement possible.
The objective is not compliance. It is curiosity. (Goleman, 2004)
Notes: Traditional models assume leaders overcome barriers through positional authority and mandate. Leading the Digital Skills Framework without line management control meant relying instead on influence and emotional intelligence (Goleman, D. (2004) 'What Makes a Leader?', Harvard Business Review, 82(1), pp. 82-91). When staff anxiety about the diagnostic audits emerged as a barrier, a manager with authority could have ordered compliance. That option was not available, and would not have worked. Overcoming it required listening to the fear and responding structurally, through the staff-hold-their-own-data model, which built the psychological safety needed for honest engagement. The objective is not compliance but curiosity: staff who want to improve, and who will tell me where I can be useful.

## Slide 7
Diagnosing the real barrier
AC2.3
1
Looked like resistance
Staff were not adopting advanced pedagogical tools.
2
Diagnostics said otherwise
Baseline data showed a foundational digital skills deficit.
3
So the project pivoted
Pause the wider framework, secure the foundations, deliver targeted resources.
If people do not understand the basic controls, no amount of advocacy for advanced tools will succeed.
Notes: A critical leadership function is diagnosing a barrier accurately before attempting to solve it. When staff did not adopt advanced pedagogical tools, the obvious reading was resistance, and the obvious response would have been more training on those tools. Baseline diagnostics established something different. The real barrier was a foundational digital skills deficit: the base on which everything else is built was not secure, and staff struggling with basic controls cannot implement advanced tools. Correctly identifying the cause allowed the project to pivot, pausing the wider framework to secure foundations and delivering targeted SharePoint resources, rather than expending energy pushing against the wrong wall. If people do not understand the basic controls, no amount of advocacy for advanced tools will succeed.

## Slide 8
Why engage stakeholders throughout
AC2.4
Engaging only at launch and closure is management by broadcast, not by influence.
1
Operational reality shifts daily
Stop engaging and you lose sight of the shifts, so timelines and support stop matching what is actually happening.
2
Engagement was the only currency I had
Without positional authority nothing could be mandated. It had to be negotiated.
3
What it bought
Heads of Area gave departmental time. Digital Leads gave a volunteer workforce and a route into every area. Century and Jisc gave diagnostic infrastructure.
Notes: Engaging stakeholders only at launch and closure is management by broadcast rather than by influence. Continuous engagement matters because operational realities in a college shift daily, and the moment you stop engaging you lose sight of those shifts. Regular contact with Heads of Area and Digital Leads is how I understand the pressures they face and adjust timelines and support accordingly. Engagement was also the only currency available to me. Without positional authority nothing could be mandated; it had to be negotiated. Engaging Heads of Area unlocked departmental time. Engaging Digital Leads secured a volunteer workforce and a specialist route into each area, translating local need to me and the direction of travel back into terms that fit local priorities. Engaging Century and Jisc provided diagnostic infrastructure and insight into how other colleges had approached the same work.

## Slide 9
Tailoring the message
AC2.4
Vice Principal
Strategic alignment and inspection compliance.
Head of Area
Operational efficiency and minimal disruption.
Teacher
Psychological safety and practical time saving.
Engagement is a source of intelligence, not a courtesy.
Engaging staff during the Jisc Discovery phase identified the foundational gap. It did not communicate the plan. It changed the plan.
Notes: Communication must address the specific needs of each constituency (Freeman, R.E. (1984) Strategic Management: A Stakeholder Approach, Pitman, Boston). A Vice Principal needs strategic alignment and inspection compliance; a Head of Area needs operational efficiency and minimal disruption; a teacher needs psychological safety and practical time saving. The strongest argument for engaging throughout, however, is that stakeholders are a feedback loop. Engagement is a source of intelligence, not a courtesy. It was through engaging staff during the initial Jisc Discovery phase that the foundational skills gap was identified. That engagement did not simply communicate the plan; it changed it, forcing a pivot toward the digital foundations work on accessibility and inclusion, and toward asynchronous SharePoint resources staff could use in their own time.

## Slide 10
Distributed resilience
Sustainable change in this sector means moving beyond models that assume formal authority.
Understand the constraints, embed through peer networks, and engage continuously rather than episodically.
Notes: Sustainable change in this sector requires moving beyond textbook models that assume formal authority. I held none, so influence had to substitute for mandate. By understanding external constraints, embedding change through peer-to-peer networks such as the Digital Leads, and engaging stakeholders continuously rather than episodically, it is possible to build genuine distributed resilience.