## 513 - Learner Sequence of Learn
#VALUE! | Unit title | Managing Projects to Achieve Results (2022) |  | Qualification title | CMI Level 5 Diploma in Management and Leadership (5D30) |  |  | #VALUE!
| Unit reference (Mindful) | 513/2022 |  | Qualification number | QAN: 603/2392/9
| Unit title and reference (CMI) | Managing Projects to Achieve Results (513) |  | Regulated qualification level | Level 5
| No. of lessons | 5 |  | About this unit | The ability to manage projects is a vital skill for all managers. This unit focuses on the knowledge and skills required to manage projects successfully and overcome problems and challenges. It requires the learner to evaluate the methods and tools for planning tasks and activities, as well as know how to implement and manage project activities, build stakeholder relationships, manage resources and risk, monitor progress, and report on outcomes.
| TUT (total unit time) | 60
| GLH (guided learning hours) | 24
| Credit value | 6
| Learning outcomes | LO1 Understand the role of projects in delivering organisational strategy LO2 Understand processes for initiating, planning and managing projects LO3 Understand the factors which contribute to effective project management |  | Lessons | 1. What is a Project? 2. Project Context and Selection 3. Project Management Methodologies 4. Project Monitoring and Review 5. Managing Projects and Project Risk
Lessons | Topics |  | Unit assessment criteria (inc. learning outcomes) | VLE content: Learner |  |  |  | Apprenticeship mapping (Level 5 Operations Manager standard ST0385 v1.4)
|  |  |  | Learn | Test | Apply | Insights | Standards | EPA link
1. What is a Project? | What is a Project? |  | 2. Understand processes for initiating, planning and managing projects 2.1 Analyse the process for initiating projects | This lesson explores the fundamentals of project management – what defines a project and the 'project lifecycle'. 3 videos present the topics and concepts There are no information sheets in this lesson | 6 self-check questions reflect the key themes covered, including the characteristics that differentiate projects from 'business as usual', the phases of the project lifecycle, practical elements of project management, and SMART project objectives. | Exercise 1: The Role of Projects Learners will identify the characteristics of a project and the role different projects play in delivering organisational strategy. Exercise 2: Initiating a Project Learners will consider how to create a project initiation document. | Resources are provided to support the content of this lesson: Gulec, R. (2014). Why are projects initiated? GreyCampus. Morphy, T. (2022). PID – Project initiation document. Stakeholdermap.com. | K8: How to identify and manage organisational improvement opportunities K9: Project management tools and techniques | Project with report Project scope and planning (K8) Project implementation (K9)
The Project Lifecycle – First 2 Stages
The Project Lifecycle – Last 3 Stages
2. Project Context and Selection | Organisational Framework |  | 1. Understand the role of projects in delivering organisational strategy 1.1 Analyse the role of projects in delivering organisational strategy 2. Understand processes for initiating, planning and managing projects 2.2 Examine the impact of legal, organisational and ethical factors on projects | This lesson takes a detailed look at a project's internal and external environment and ways to analyse its feasibility by examining organisational frameworks, environmental context and project selection methods. 4 videos present the topics and concepts 2 information sheets build on the learning in detail | 8 self-check questions reflect the key themes covered in the videos, including forms of project organisation, building a business case for a project, return on investment, internal and external project stakeholders, the 'PESTEL' framework, and problem-solving and decision-making techniques. | Exercise 1: Factors that Impact Projects Learners will consider the impact of legal, organisational and ethical factors on a project. Exercise 2: Working Collaboratively with Stakeholders Learners will identify internal and external stakeholders for a project scenario and identify specific techniques most suited to working collaboratively with them to achieve the aims of the project. | Resources are provided to support the content of this lesson: Guinan, B. (2024). External and internal factors affecting project management. BrightWork Blog. Government Communication Service (2021). Ensuring effective stakeholder management. | K8: How to identify and manage organisational improvement opportunities K9: Project management tools and techniques K12: Problem-solving and decision-making techniques | Project with report Project scope and planning (K8) Project implementation (K9, K12)
The Project Environment – Stakeholders
The Project Environment – External Influences
Project Selection Methods
Problem-solving and Decision-making
Decision Trees
3. Project Management Methodologies | What is Project Management Methodology? |  | 2. Understand processes for initiating, planning and managing projects 2.3 Discuss the use of tools and techniques to plan and manage projects in different contexts 2.4 Analyse techniques for working collaboratively with stakeholders to achieve project aims | This lesson lesson focuses on project management methodologies and their applications. It examines structured project management, agile project management and the PRINCE2 framework. 5 videos present the topics and concepts There are no information sheets in this lesson | 10 self-check questions reflect the key themes covered in the videos, including the 'waterfall', 'critical path' and 'structured systems analysis and design' methods, 'Parkinson's Law', 'scrum meetings', principles, and themes and processes of the PRINCE2 methodology. | Exercise 1: Structured and Agile Project Management Methodologies Learners will provide a summary of these two approaches that identifies their benefits and drawbacks and when it is ideal to use them. Exercise 2: Project Methodologies in Context Learners will select one methodology to research in detail and prepare a summary to include in a project management handbook. | Resources are provided to support the content of this lesson: TeamGantt (N.D.). What is a Gantt chart? A practical guide for project managers. Hoban, S. M. (2024). What is a work breakdown structure in project management? | K5: IT and software tools used to support the current and future needs of the organisation, including advances in technology K9: Project management tools and techniques | Project with report Project implementation (K5, K9)
Structured Project Management Methodologies – Part 1
Structured Project Management Methodologies – CCPM
Agile Project Management
PRINCE2
4. Project Monitoring and Review | Monitoring Tasks, Costs and People |  | 2. Understand processes for initiating, planning and managing projects 2.5 Evaluate methods used for monitoring project progress 2.6 Discuss methods for reporting on project outcomes 3. Understand the factors which contribute to effective project management 3.1 Discuss methods of managing data and information in a project environment | This lesson explores ways of monitoring a project, including the meetings and metrics required to accurately review project progress. It will also look at the reasons why some projects don't go to plan and what can be done to get them back on track, covering the use of key performance indicators (KPIs). 4 videos present the topics and concepts 4 information sheets build on the learning in detail | 8 self-check questions reflect the key themes covered in the videos, including the 'time, cost and quality triangle', 'scope creep', 'pulse meetings', project governance best practice, financial and non-financial metrics, KPIs, the role of the project management office, and criteria for assessing data quality. | Exercise 1: Monitoring Project Progress – Applying Metrics Learners will identify business-focused metrics and specific KPIs suitable for monitoring the progress of an existing project. Exercise 2: Reporting on Project Outcomes Learners will identify different methods of reporting on project outcomes and consider their benefits and drawbacks. | Resources are provided to support the content of this lesson: Morphy, T. (2024). Project management monitoring and control techniques. Stakeholdermap.com. Malsam, W. (2024). 7 Steps to project closure. ProjectManager. | K1: Presentation skills and methods K6: Methods for researching, analysing, interpreting and evaluating data to inform judgements and enable decision-making K9: Project management tools and techniques | Project with report Project scope and planning (K6) Project implementation (K9) Evaluation and recommendations (K1)
Meetings, Tools and Metrics to Review Project Progress
Using Software to Facilitate Project Planning
Applying Metrics, KPIs, Dashboards and the Role of Health Checks
Reporting on Your Project
Using Data and Information
Analysing and Summarising Quantitative Data
The Role of the Project Management Office
5. Managing Projects and Project Risk | Identifying Risk |  | 2. Understand processes for initiating, planning and managing projects 2.7 Assess approaches for project closure 3. Understand the factors which contribute to effective project management 3.2 Assess the use of problem-solving and decision-making techniques when managing projects 3.3 Examine approaches to identify, manage and mitigate project risks | This lesson looks specifically at project risks, covering identification, assessment and mitigation. It also explores why projects succeed or fail. 4 videos present the topics and concepts There are no information sheets in this lesson | 8 self-check questions reflect the key themes covered in the videos, including tools to help identify risks, 'confirmation bias', 'HAZOP' process for risk assessment, the Kinney–Wiruth model of risk assessment, steps for mitigating risk, and Elbeik and Thomas' ten indicators of success. | Exercise 1: Identifying, Managing and Mitigating Project Risks Learners will provide an overview of a risk management process suitable for presentation at a management meeting. Exercise 2: Assessing Risk Learners will conduct a subjective risk assessment and consider how to manage and mitigate the risks identified. | Resources are provided to support the content of this lesson: Handout – Perception of Risk Pradip, P. (2023). What is an issue log? Simplilearn. | K9: Project management tools and techniques K12: Problem-solving and decision-making techniques K21: Business continuity principles, including risk assessment, contingency planning and disaster recovery | Project with report Project implementation (K9, K12) Professional discussion underpinned by a portfolio of evidence Operational planning (K21)
Assessing Risk
Risk Management and Mitigation
Why Projects Succeed or Fail

## 513 - CMI x Ops Manager Mapping
#VALUE! | Unit title | Managing Projects to Achieve Results (2022) | Qualification title | CMI Level 5 Diploma in Management and Leadership (5D30) |  | #VALUE!
| Unit reference (Mindful) | 513/2022 | Qualification number | QAN: 603/2392/9
| Unit title and reference (CMI) | Managing Projects to Achieve Results (513) | Regulated qualification level | Level 5
| No. of lessons | 5 | About this unit | The ability to manage projects is a vital skill for all managers. This unit focuses on the knowledge and skills required to manage projects successfully and overcome problems and challenges. It requires the learner to evaluate the methods and tools for planning tasks and activities, as well as know how to implement and manage project activities, build stakeholder relationships, manage resources and risk, monitor progress, and report on outcomes.
| TUT (total unit time) | 60
| GLH (guided learning hours) | 24
| Credit value | 6
| Learning outcomes | LO1 Understand the role of projects in delivering organisational strategy LO2 Understand processes for initiating, planning and managing projects LO3 Understand the factors which contribute to effective project management | Lessons | 1. What is a Project? 2. Project Context and Selection 3. Project Management Methodologies 4. Project Monitoring and Review 5. Managing Projects and Project Risk
Learning outcomes | Assessment criteria | Indicative content |  | Mapped to online lessons | Apprenticeship mapping (Level 5 Operations Manager standard ST0385 v1.4)
[5 empty] | Standards | EPA link
1. Understand the role of projects in delivering organisational strategy | 1.1 Analyse the role of projects in delivering organisational strategy | Role may include but is not limited to: - definitions of term ‘project’ - projects vs BAU (business as usual) - delivering organisation’s strategy - achieving competitive advantage - innovation - supporting decision-making - enabling change |  | Lesson 2 | K8: How to identify and manage organisational improvement opportunities K9: Project management tools and techniques K12: Problem-solving and decision-making techniques | Project with report Project scope and planning (K8) Project implementation (K9, K12)
2. Understand processes for initiating, planning and managing projects | 2.1 Analyse the process for initiating projects | Process refers to process management and may include but is not limited to: - the creation of project initiation documents - defining purpose - objectives - key performance indicators (KPIs) - scope - deliverables - constraints - quality - assumptions - development of formal business case - success criteria - resource requirements (people, finance, equipment, time) - cost–benefit analysis (CBA) - risk analysis and assessment - defining project organisation - project team roles - stakeholder analysis - communications strategy - selecting technology |  | Lesson 1 | K1: Presentation skills and methods K5: IT and software tools used to support the current and future needs of the organisation, including advances in technology K6: Methods for researching, analysing, interpreting and evaluating data to inform judgements and enable decision-making K8: How to identify and manage organisational improvement opportunities K9: Project management tools and techniques K12: Problem-solving and decision-making techniques K21: Business continuity principles, including risk assessment, contingency planning and disaster recovery | Project with report Project scope and planning (K6, K8) Project implementation (K5, K9, K12) Evaluation and recommendations (K1) Professional discussion underpinned by a portfolio of evidence Operational planning (K21)
| 2.2 Examine the impact of legal, organisational and ethical factors on projects | Legal may include but is not limited to: - Health and Safety at Work etc. Act 1974 - General Data Protection Regulation 2018 - Freedom of Information Act 2000 - Sale of Goods Act 1979 - Equality Act 2010 - Digital Economy Bill 2016 - Working Time Directive 1998 - Safeguarding Vulnerable Groups Act (SVGA) 2006 - Communication Act 2003 |  | Lesson 2
Organisational refers to data security and management and may include but is not limited to: - performance standards - customer service charters - HR and health and safety policies - safety and security - information security - confidentiality - conflict of interest - equality and diversity - communication - knowledge-sharing protocols - procurement policies and procedures - risk assessment - 'lean' production - quality standards and policies - whistleblowing
Ethical may include but is not limited to: - code of conduct - sustainability - corporate social responsibility - organisational values and culture - equality and diversity
| 2.3 Discuss the use of tools and techniques to plan and manage projects in different contexts | Tools and techniques refers to how to set up, plan, organise and manage a project and resources using relevant tools and techniques and may include but are not limited to: - Gantt charts - milestone charts - network diagrams - project plans - critical path analysis (CPA) - work breakdown structure (WBS) - project methodologies (e.g. PRINCE2 or other organisation-specific methodologies) |  | Lesson 3
Different contexts may include but are not limited to: - projects of different sizes, levels of risk and complexity - internal or external - timescales - series of projects or one of a kind - project types (e.g. administrative, construction, IT, equipment or system installation, event or relocation, new product or service development, research, Human Resource management/restructure)
| 2.4 Analyse techniques for working collaboratively with stakeholders to achieve project aims | Techniques may include but are not limited to: - identifying needs - building consensus - agreeing shared goals - creating communications plans/approaches - clarifying roles and responsibilities - empowering others
Stakeholders refers to work collaboratively with others both inside and outside of the organisation and may include but are not limited to: - internal – team members, line managers, senior managers, board members - external – customers, pressure groups, government agencies - connected – suppliers, partners, contractors
| 2.5 Evaluate methods used for monitoring project progress | Methods used for monitoring against the project plan and may include but are not limited to: - time, quality and cost outputs - maintaining logs of quality issues and exceptions - planned vs actual monitoring forms - project meetings and huddles - risk review |  | Lesson 4
Evaluating may include but is not limited to performance (qualitative and quantitative) against outcomes
| 2.6 Discuss methods for reporting on project outcomes | Methods refer to the effective use of technology in an organisation and the production of reports providing management information
Methods may include but are not limited to other forms of communication such as: - newsletters - notice boards - letters, memos - emails - briefings and meetings - presentations and briefings - video conferencing - intranet - emails - blogs - discussion forums - podcasts and webinars
| 2.7 Assess approaches for project closure | Approaches may include but are not limited to: - administrative closure (e.g. handover, team celebration, feedback from stakeholders, lessons learned/good practice workshops, re-allocating resources, finalising accounts, archiving data and information, knowledge management, post-implementation review (PIR)) - contract closure (e.g. terms and conditions, exit criteria). |  | Lesson 5
3. Understand the factors which contribute to effective project management | 3.1 Discuss methods of managing data and information in a project environment | Data and information refers to the effective use of technology in an organisation, data security and management and the collation, analysis and interpretation of data |  | Lesson 4 | K1: Presentation skills and methods K6: Methods for researching, analysing, interpreting and evaluating data to inform judgements and enable decision-making K9: Project management tools and techniques K12: Problem-solving and decision-making techniques K21: Business continuity principles, including risk assessment, contingency planning and disaster recovery | Project with report Project scope and planning (K6) Project implementation (K9, K12) Evaluation and recommendations (K1) Professional discussion underpinned by a portfolio of evidence Operational planning (K21)
May include but are not limited to assessing characteristics of data and information: - accuracy - validity - reliability - timeliness - relevance - completeness
| 3.2 Assess the use of problem-solving and decision-making techniques when managing projects | Problem solving and decision making techniques may include but are not limited to: - root cause analysis - fishbone analysis (Ishikawa, c.1960s) - 'plan, do, check act' cycle (PDCA) (Deming, c.1950s) - Pareto Principle (Juran, c.1937) - cost–benefit analysis (CBA) - return on investment (ROI) - options appraisal - 'OODA Loop' (Boyd, 1998) - PMI ('plus, minus, interesting') (De Bono, 2002) - Ladder of Inference (Senge, 2006) |  | Lesson 5
| 3.3 Examine approaches to identify, manage and mitigate project risks | Identify and manage may include but are not limited to: - monitoring and managing costs in respect of expected and unexpected loss - net social cost–benefit - employing risk mitigation techniques - improving ICT systems and procedures - up-skilling staff - avoiding high risks - monitoring risk using effective risk reporting - senior management involvement - stress testing - event analysis
Mitigating may include but is not limited to: - transferring risk - use of insurance policies - contingency planning - disaster planning - alternative risk transfer - risk avoidance - minimisation - prevention and prediction of risk

## 513 - Ops Manager Mapping
#VALUE! | Unit title | Managing Projects to Achieve Results (2022) | Qualification title | Mapped to CMI Level 5 Diploma in Management and Leadership (5D30) and Operations Manager standard ST0385 v1.4 |  | #VALUE!
| Unit reference | 513/2022 | Regulated qualification level | Level 5
| No. of lessons | 5 | About this unit | The ability to manage projects is a vital skill for all managers. This unit focuses on the knowledge and skills required to manage projects successfully and overcome problems and challenges. It requires the learner to evaluate the methods and tools for planning tasks and activities, as well as know how to implement and manage project activities, build stakeholder relationships, manage resources and risk, monitor progress, and report on outcomes.
| GLH (guided learning hours) | 24
| Learning outcomes | Project scope and planning Project implementation Evaluation and recommendations Operational planning
| Lessons | 1. What is a Project? 2. Project Context and Selection 3. Project Management Methodologies 4. Project Monitoring and Review 5. Managing Projects and Project Risk
Learning outcomes | Knowledge topics | Indicative content |  | Mapped to online lessons | Apprenticeship mapping (Level 5 Operations Manager standard ST0385 v1.4)
[5 empty] | Standards | EPA link
Project scope and planning Project implementation | Analyse the role of projects in delivering organisational strategy | Role may include but is not limited to: - definitions of term ‘project’ - projects vs BAU (business as usual) - delivering organisation’s strategy - achieving competitive advantage - innovation - supporting decision-making - enabling change |  | Lesson 2 | K8: How to identify and manage organisational improvement opportunities K9: Project management tools and techniques K12: Problem-solving and decision-making techniques | Project with report Project scope and planning (K8) Project implementation (K9, K12)
Project scope and planning Project implementation Evaluation and recommendations Operational planning | Analyse the process for initiating projects | Process refers to process management and may include but is not limited to: - the creation of project initiation documents - defining purpose - objectives - key performance indicators (KPIs) - scope - deliverables - constraints - quality - assumptions - development of formal business case - success criteria - resource requirements (people, finance, equipment, time) - cost–benefit analysis (CBA) - risk analysis and assessment - defining project organisation - project team roles - stakeholder analysis - communications strategy - selecting technology |  | Lesson 1 | K1: Presentation skills and methods K5: IT and software tools used to support the current and future needs of the organisation, including advances in technology K6: Methods for researching, analysing, interpreting and evaluating data to inform judgements and enable decision-making K8: How to identify and manage organisational improvement opportunities K9: Project management tools and techniques K12: Problem-solving and decision-making techniques K21: Business continuity principles, including risk assessment, contingency planning and disaster recovery | Project with report Project scope and planning (K6, K8) Project implementation (K5, K9, K12) Evaluation and recommendations (K1) Professional discussion underpinned by a portfolio of evidence Operational planning (K21)
| Examine the impact of legal, organisational and ethical factors on projects | Legal may include but is not limited to: - Health and Safety at Work etc. Act 1974 - General Data Protection Regulation 2018 - Freedom of Information Act 2000 - Sale of Goods Act 1979 - Equality Act 2010 - Digital Economy Bill 2016 - Working Time Directive 1998 - Safeguarding Vulnerable Groups Act (SVGA) 2006 - Communication Act 2003 |  | Lesson 2
Organisational refers to data security and management and may include but is not limited to: - performance standards - customer service charters - HR and health and safety policies - safety and security - information security - confidentiality - conflict of interest - equality and diversity - communication - knowledge-sharing protocols - procurement policies and procedures - risk assessment - 'lean' production - quality standards and policies - whistleblowing
Ethical may include but is not limited to: - code of conduct - sustainability - corporate social responsibility - organisational values and culture - equality and diversity
| Discuss the use of tools and techniques to plan and manage projects in different contexts | Tools and techniques refers to how to set up, plan, organise and manage a project and resources using relevant tools and techniques and may include but are not limited to: - Gantt charts - milestone charts - network diagrams - project plans - critical path analysis (CPA) - work breakdown structure (WBS) - project methodologies (e.g. PRINCE2 or other organisation-specific methodologies) |  | Lesson 3
Different contexts may include but are not limited to: - projects of different sizes, levels of risk and complexity - internal or external - timescales - series of projects or one of a kind - project types (e.g. administrative, construction, IT, equipment or system installation, event or relocation, new product or service development, research, Human Resource management/restructure)
| Analyse techniques for working collaboratively with stakeholders to achieve project aims | Techniques may include but are not limited to: - identifying needs - building consensus - agreeing shared goals - creating communications plans/approaches - clarifying roles and responsibilities - empowering others
Stakeholders refers to work collaboratively with others both inside and outside of the organisation and may include but are not limited to: - internal – team members, line managers, senior managers, board members - external – customers, pressure groups, government agencies - connected – suppliers, partners, contractors
| Evaluate methods used for monitoring project progress | Methods used for monitoring against the project plan and may include but are not limited to: - time, quality and cost outputs - maintaining logs of quality issues and exceptions - planned vs actual monitoring forms - project meetings and huddles - risk review |  | Lesson 4
Evaluating may include but is not limited to performance (qualitative and quantitative) against outcomes
| Discuss methods for reporting on project outcomes | Methods refer to the effective use of technology in an organisation and the production of reports providing management information
Methods may include but are not limited to other forms of communication such as: - newsletters - notice boards - letters, memos - emails - briefings and meetings - presentations and briefings - video conferencing - intranet - emails - blogs - discussion forums - podcasts and webinars
| Assess approaches for project closure | Approaches may include but are not limited to: - administrative closure (e.g. handover, team celebration, feedback from stakeholders, lessons learned/good practice workshops, re-allocating resources, finalising accounts, archiving data and information, knowledge management, post-implementation review (PIR)) - contract closure (e.g. terms and conditions, exit criteria). |  | Lesson 5
Project scope and planning Project implementation Evaluation and recommendations Operational planning | Discuss methods of managing data and information in a project environment | Data and information refers to the effective use of technology in an organisation, data security and management and the collation, analysis and interpretation of data |  | Lesson 4 | K1: Presentation skills and methods K6: Methods for researching, analysing, interpreting and evaluating data to inform judgements and enable decision-making K9: Project management tools and techniques K12: Problem-solving and decision-making techniques K21: Business continuity principles, including risk assessment, contingency planning and disaster recovery | Project with report Project scope and planning (K6) Project implementation (K9, K12) Evaluation and recommendations (K1) Professional discussion underpinned by a portfolio of evidence Operational planning (K21)
May include but are not limited to assessing characteristics of data and information: - accuracy - validity - reliability - timeliness - relevance - completeness
| Assess the use of problem-solving and decision-making techniques when managing projects | Problem solving and decision making techniques may include but are not limited to: - root cause analysis - fishbone analysis (Ishikawa, c.1960s) - 'plan, do, check act' cycle (PDCA) (Deming, c.1950s) - Pareto Principle (Juran, c.1937) - cost–benefit analysis (CBA) - return on investment (ROI) - options appraisal - 'OODA Loop' (Boyd, 1998) - PMI ('plus, minus, interesting') (De Bono, 2002) - Ladder of Inference (Senge, 2006) |  | Lesson 5
| Examine approaches to identify, manage and mitigate project risks | Identify and manage may include but are not limited to: - monitoring and managing costs in respect of expected and unexpected loss - net social cost–benefit - employing risk mitigation techniques - improving ICT systems and procedures - up-skilling staff - avoiding high risks - monitoring risk using effective risk reporting - senior management involvement - stress testing - event analysis
Mitigating may include but is not limited to: - transferring risk - use of insurance policies - contingency planning - disaster planning - alternative risk transfer - risk avoidance - minimisation - prevention and prediction of risk